**State Plan for Aging Services 2023-2027**

**General Timeline**

|  |  |
| --- | --- |
| **Activity** | **Timeframe** |
| State Plan Needs Assessment – Focus Groups | August – September |
| Intrastate Funding Formula – Meetings | August – October |
| State Plan Needs Assessment – Survey Collection and Analysis | August – November |
| Outreach and Collect Virginia State Agency Reports | October – December |
| Write State Plan | December – February |
| DEADLINE: Share Draft State Plan Parts with ACL for Pre-Review and Feedback | January 2023 |
| DEADLINE: Complete Work on Writing the Draft State Plan | February 15, 2023 |
| DEADLINE: Post Draft State Plan on DARS Website for Public Comment Period | February 15 – March 15, 2023 |
| DEADLINE: Submit Draft State Plan for Administration Approvals | May 1, 2023 |
| HARD DEADLINE: Formally Submit State Plan to ACL for Formal ACL Approval | July 1, 2023 |
| HARD DEADLINE: Post State Plan on Town Hall Website for 30-day Public Comment Period | August 1, 2021 |
| HARD DEADLINE: Submit State Plan to General Assembly & Governor as required by the Code of Virginia | October 1, 2023 |
| New State Plan starts as required by Older Americans Act | October 1, 2023 |
| New State Plan starts as required by the Code of Virginia | October 1, 2023 |